## Slide 1: DG Justice and Consumers
Project Modifications
DG Justice and Consumers

## Slide 2: Changes
are exceptions
may not substantially modify the project
must have an EU added value
shall respect the principle of equality of treatment of applicants
shall comply with the provisions of the Justice programme, the call for proposals and the grant agreement
may not increase the maximum grant amount or co-financing rate

## Slide 3: Provisions in Grant Agreements
Amendments to the agreement – Article II.12
Budget transfers not exceeding 20% of a budget category (heading) – Articles II.22 and I.12
Additional sub-contracting – Article I.9
Staff changes – Article I.14

## Slide 4: Requests
    Check pages 40-42 of the Guide for Action Grants
    WHO ?
     legal representative or contact person of the coordinator on behalf of the whole partnership
    WHEN ?
    before the change takes effect and at least one month before the end of the eligibility period
    HOW
     in writing
     justification
    supporting documents

## Slide 5: 20% Rule
20% increase of the heading for which the transfer is intended
Indirect costs (Heading F) may not be increased
Costs must be eligible (Article II.19)
  Indicated in the estimated budget
  Necessary
  Reasonable
  Incurred during the eligibility period, recorded in the accounts, etc.

## Slide 6: 20% Rule
The action must be implemented as described in Annex I
  Activities and outputs may not be reduced/cancelled to free funds
Changes are cumulative
  Monitor your expenses and these of your co-beneficiaries closely
  Report expenses in the initial estimated budget/financial statement (Annex III to the agreement)
  The Commission will check that no budget heading has been increased by more than 20% after reception of the final report
Transfers of costs within a budget heading are possible
Transfers of costs from one co-beneficiary to another are possible

## Slide 7: 20% Rule - Examples
Allowed
  Higher number of participants to training activities
  Additional project meeting – if justified
  Increased cost of a budget item
Questionable
  Increase of budget heading A – staff costs
Not allowed
    Costs not indicated in the estimated budget

## Slide 8: Non-substantial Changes in the Activities
What is allowed - examples
  Swap of venues of project meetings
  Adaptation of the date of events or length of workstream, within eligibility period
What is questionable - examples
  Meetings moved to non-participating countries
  Too many representatives of co-beneficiaries at project events
  Transfer of an activity from one co-beneficiary to another
Not allowed
  Change of methodology, change of target groups, etc.
  Change of venue of major events

## Slide 9: Administrative Changes
Change of legal address of coordinator/ beneficiary
Change of bank account of coordinator
Change of legal representative of coordinator
Change of contact person/contact details
Statutory change of coordinator/ beneficiary
New associate partner
Check the list of supporting documents in the Guide for Action Grants

## Slide 10: Formal Amendment
  Addition/withdrawal of a co-beneficiary
  Implementation period of the project
  Budget changes exceeding 20% of a budget heading
  Adaptation of Annex I

## Slide 11: Recommendations
    Check the agreement and the Guide for Action Grants
    Collect the relevant documents
      See pages 40 to 42 in the Guide for Action Grants
    Be precise when you contact the Commission
      Agreement number
      Workstream number
      Activity or output number
      Budget line number
      Event/publication name
    Limit changes
    File all the relevant documents with your agreement

## Slide 12
    Thank you for your attention !